## Sprint Backlog
Sprint <#> Backlog
ID | Name | Story | Importance | Estimated Man-Hours | Dependance | Test Cases | Notes | State

## Task Boards
Sprint <#> Task Boards
Sprint Number:
Sprint Start Date:
Sprint End Date:
ID# Story Name (man-hours)
Task Name | Assigned to | Deadline | Completed Date | Note
ID# Story Name (man-hours) |  | #1 Deposit (5)
Task Name | Assigned to | Deadline | Completed Date | Note
Create transaction table | Student A | 2025-02-01
Create data access layer | Student B | 2025-02-10
Implement deposit function | Student B | 2025-02-10
Implement balance calculation | Student B | 2025-02-10
Create deposit UI | Student C & Student D | 2025-02-20
Create balance UI | Student C & Student D | 2025-02-20
*** This is a SAMPLE. Create a task board for each story. ***

## Burndown Chart
Sprint <#> Burndown Chart
Day | Date | Happy Path Completion | Team Completion | Story Man-Hours Completed
0 | 2025-02-06 | 50 | 50 | 0
1 | 2025-02-07 | 47.3684 | 50 | 0
2 | 2025-02-08 | 44.7368 | 50 | 0
3 | 2025-02-09 | 42.1053 | 50 | 0
4 | 2025-02-10 | 39.4737 | 50 | 0
5 | 2025-02-11 | 36.8421 | 50 | 0
6 | 2025-02-12 | 34.2105 | 50 | 0
7 | 2025-02-13 | 31.5789 | 50 | 10
8 | 2025-02-14 | 28.9474 | 40 | 0
9 | 2025-02-15 | 26.3158 | 40 | 0
10 | 2025-02-16 | 23.6842 | 40 | 7
11 | 2025-02-17 | 21.0526 | 33 | 8
12 | 2025-02-18 | 18.4211 | 25 | 0
13 | 2025-02-19 | 15.7895 | 25 | 0
14 | 2025-02-20 | 13.1579 | 25 | 8
15 | 2025-02-21 | 10.5263 | 17 | 0
16 | 2025-02-22 | 7.8947 | 17 | 0
17 | 2025-02-23 | 5.2632 | 17 | 10
18 | 2025-02-24 | 2.6316 | 7 | 0
19 | 2025-02-25 | -2.4869e-14 | 7 | 0
Total Man-Hours in the Sprint: |  |  |  | 50
Total Days in the Sprint: |  |  |  | 19